## Dashboard
GUARDIAN / EXECUTION SCORECARD
Pilot: Oct 19 – Nov 29, 2026 • Enter actual evidence in the supporting sheets; targets are hypotheses, not forecasts.
KPI | Actual | G6 target | Gate result | Source | Interpretation
Qualified interviews |  | 8 |  | Interview Log | Developers using 2+ coding sessions recently
Recent pain validated |  | 5 |  | Interview Log | Specific coordination incident within 30 days
Alpha testers completed |  | 4 |  | Alpha Testers | 4 of 5 target testers finish guided workflow
Verified unique installs |  | 50 |  | Weekly Metrics | Unique first-time installs, not download count
Activated users |  | 15 |  | Weekly Metrics | Generated a risk report successfully
Repeat users |  | 8 |  | Weekly Metrics | Used on a separate day/session; count once
Paying customers |  | 3 |  | Weekly Metrics | Genuine customers; refunds excluded
Critical safety incidents |  | 0 |  | Weekly Metrics | Zero tolerated
Activation rate |  | 30% |  | Calculated | Target heuristic: 30%+ of installs
Repeat rate |  | 50% |  | Calculated | Target heuristic: 50%+ of activated
Paid conversion of activated |  | 20% |  | Calculated | Target heuristic: 20%+ of activated
Gross revenue (USD) |  |  |  | Weekly Metrics | Collected gross; not profit
Net receipts (USD) |  |  |  | Weekly Metrics | Gross less refunds and payment fees
READOUT / HOW TO USE
1. Set weekly actuals and evidence; never populate metrics with aspirational numbers.
2. Update milestone gate status only after collecting evidence and reviewing pass criteria.
3. Interview results are counted from Interview Log; alpha completion from Alpha Testers.
4. Distinct user counts must be deduplicated across weeks; opt-in/self-reported is acceptable.
5. Safety incident >0 blocks public rollout regardless of other KPIs.
6. At G6 choose Scale / Iterate / Pivot / Stop in Decision Log.

## Milestones
MILESTONE GATES
A gate cannot pass simply because its tasks are marked complete. Attach evidence and record the founder's decision.
Gate | Week / dates | Delivery | Evidence-based exit criteria | Owner | Status | Evidence URL / path | Decision / notes
G1 | Oct 19–25 | Research and charter | >=10 competitors; >=8 interviews; >=5 describe recent pain; PRD frozen | Founder | Done | docs/RESEARCH_G1.md | Closed 2026-10-17 by desk research (10 sourced pain points, 20-tool matrix). Interview round dropped by founder on 2026-10-20; H1 accepted on desk research + founder incidents. GO to G2 with wedge = task ownership + preflight overlap.
G2 | Oct 26–Nov 1 | Local prototype | Inspection + task claims + risk/handoff; >=20 fixtures; no surprise writes | Engineering / founder review | Done | docs/SAFETY_AUDIT.md; tests/ (19 CLI + 16 mod + hook); CI green; demo/scenarios.sh; tag v0.1.0 | Closed 2026-10-20, ahead of the Oct 26–Nov 1 window. All five deliverables with evidence. Demo recordings (G2-09) prepared via demo/scenarios.sh; the clips themselves are the founder's. Windows support added 2026-10-23 (CLI 0.2.1, mod 0.17.0), CI green on ubuntu+macos+windows at 7007167.
G3 | Nov 2–8 | Private alpha | >=5 testers; >=4 completed guided flow; 0 critical incidents | Founder | Ready — awaiting testers | docs/ALPHA_GUIDE.md; docs/ALPHA_OUTREACH.md | Everything a tester needs exists. Exit needs 5 real testers observed; cannot be closed without them.
G4 | Nov 9–15 | Public free beta | Tagged release, guides, privacy, demo; 0 known P0/P1 issues | Founder | Ready — awaiting launch | CHANGELOG.md; docs/PRIVACY.md; docs/RELEASE_CHECKLIST.md; .github/ISSUE_TEMPLATE; release v0.1.0 | Public repo, tagged release, docs, privacy, issue templates done. Exit needs the directory submission, demo clips posted, and ≥50 verified installs measured.
G5 | Nov 16–22 | Paid-value test | Checkout/fulfillment tested; clear differentiation; real buyer feedback | Founder | Ready — awaiting build + checkout | docs/PRICING.md | Free/Pro boundary, two price messages, checkout/fulfilment/refund plan written. Exit needs Pro features behind a license, a live checkout, and real buyers.
G6 | Nov 23–29 | Continue/pivot decision | >=50 installs; >=15 activated; >=8 repeat; >=3 paying; safe operation | Founder | Template ready | docs/DECISION_MEMO.md | Memo template with thresholds and formulas. Exit is the dated decision on 2026-11-29 with frozen metrics.

## Backlog
DELIVERY BACKLOG
Update owner, status, evidence, and blockers. 'Done' requires acceptance evidence—not only an AI claim.
Task ID | Gate | Priority | Deliverable / ticket | Owner | Due | Status | Acceptance / done condition | Evidence link | Blocker / notes
G1-01 | G1 | P0 | Competitive matrix: >=10 tools | Founder | 2026-10-22 | Done | Features, price, links, gaps verified | docs/RESEARCH_G1.md §2 | 20 tools, A–D columns verified/unverified
G1-02 | G1 | P0 | Recruit 8–10 qualified interviewees | Founder | 2026-10-23 | Dropped | Candidates used 2+ agent sessions in last month | docs/MASTER_PLAN.md §15 | Founder decision 2026-10-20: desk research + own incidents replace interviews
G1-03 | G1 | P0 | Conduct problem interviews | Founder | 2026-10-25 | Dropped | >=8 notes; >=5 recent incidents for H1 | docs/MASTER_PLAN.md §15 | see G1-02
G1-04 | G1 | P0 | PRD + go/no-go decision | Founder | 2026-10-25 | Done | Scope and unmet value wedge written | docs/RESEARCH_G1.md §5; MASTER_PLAN §15 | GO to G2; wedge re-scoped
G2-01 | G2 | P0 | CLI inspect + repo/worktree model | Engineering | 2026-10-28 | Done | Works offline; read-only; documented output | src/commands/inspect.ts; tests/cli.test.ts | worktrees, locks, in-flight ops, task↔worktree map
G2-02 | G2 | P0 | Task manifest + explicit claims | Engineering | 2026-10-29 | Done | Never silently writes; validates path input | src/commands/task.ts; plugins/session-agents/hooks/tasks.ts | shared .guardian/tasks.json; mod holds edits and asks the user
G2-03 | G2 | P0 | Risk report overlapping tasks | Engineering | 2026-10-30 | Done | Catches overlap fixtures with evidence | src/lib/analyze.ts; tests/cli.test.ts | 10 finding types with fixes; suggested merge order
G2-04 | G2 | P0 | Evidence-based handoff report | Engineering | 2026-10-30 | Done | Unknown test result says 'Not verified' | src/commands/handoff.ts | verified / supplied-not-verified / not verified; tree fingerprint
G2-05 | G2 | P0 | 20+ fixtures and safety audit | Engineering / founder | 2026-11-01 | Done | All critical fixtures green; no destructive commands | docs/SAFETY_AUDIT.md; tests/ | 19 CLI + 16 mod + hook tests; audit row by row
G3-01 | G3 | P0 | Alpha onboarding and demo guide | Founder | 2026-11-03 | Done | New user can run workflow from clean clone | docs/ALPHA_GUIDE.md
G3-02 | G3 | P0 | Recruit 5 alpha testers | Founder | 2026-11-04 | Ready | Five distinct qualified volunteers | docs/ALPHA_OUTREACH.md | targets + message drafted; sending is the founder's
G3-03 | G3 | P0 | Observe 5 full workflows | Founder | 2026-11-08 | Not Started | >=4 finish, feedback recorded per tester
G4-01 | G4 | P0 | Public beta release checklist | Engineering / founder | 2026-11-11 | Done | License, docs, privacy, changelog, smoke test | docs/RELEASE_CHECKLIST.md; release v0.1.0
G4-02 | G4 | P1 | 2 short product demo videos | Founder | 2026-11-13 | Done (terminal clips) | Screens include overlap and handoff scenarios | demo/recordings/ | script ready; recordings owed
G4-03 | G4 | P1 | Launch distribution experiments | Founder | 2026-11-15 | Ready | Channels logged; follows community rules | docs/RESEARCH_G1.md §4 channel list | directory submission + Reddit/HN/X posts are the founder's
G5-01 | G5 | P0 | Paid value and pricing experiment | Founder | 2026-11-18 | In Progress | Distinct Pro benefit; non-leading buyer feedback | workspace-guardian-pro@400c0cb; src/lib/license.ts; tests/pro.test.ts | Pro 0.1.0 built + verified with a signed key 2026-10-23; checkout page and price messages still owed
G5-02 | G5 | P0 | Checkout, fulfillment, support test | Founder | 2026-11-20 | Ready — founder setup | Successful test order, delivery and policy | docs/CHECKOUT_LEMONSQUEEZY.md; workspace-guardian-pro scripts/pack.sh, scripts/fulfil.ts | engineering done 2026-10-23; store creation, test purchase and refund are the founder's
G6-01 | G6 | P0 | Cohort/funnel and safety review | Founder | 2026-11-28 | Not Started | Metrics deduplicated, evidence reviewed
G6-02 | G6 | P0 | Scale/iterate/pivot/stop memo | Founder | 2026-11-29 | Template | Decision, reasons, 30-day next actions | docs/DECISION_MEMO.md
G2-06 | G2 | P0 | Push to GitHub, CI green on ubuntu+macos, replace <owner>/<repo> | Founder / engineering | 2026-10-24 | Done | .github/workflows/ci.yml passes on both OSes | https://github.com/d10or/workspace-guardian/actions/runs/39390316230 | 3 jobs green on first push
G2-07 | G2 | P0 | Choose license (R7) and add LICENSE | Founder | 2026-10-24 | Done | LICENSE file; package.json license updated | LICENSE; package.json | MIT
G2-08 | G2 | P1 | Mod: per-session files for notes/pins/messages; version-match test | Engineering | 2026-10-30 | Done | claude plugin test green | plugins/session-agents v0.15.0; .github/workflows/ci.yml | messages per session, timer guard, version check in CI
G2-09 | G2 | P1 | Record demo: clean repo, risky overlap, safe handoff | Founder | 2026-11-01 | Done (terminal clips) | 2 short recordings | demo/recordings/*.gif; README "See it" | 3 terminal clips recorded by Claude, approved by founder 2026-10-20; the in-Claude-Code Allow/Deny clip is still the founder's
G4-04 | G4 | P2 | Free SKILL.md wrapper for the CLI listed on Agensi.io (discovery for Cursor/Codex users) | Engineering / founder | 2026-11-20 | Not Started | skill lists, points at repo + store; zero Pro content |  | after launch data exists; never Pro

## Weekly Metrics
WEEKLY METRICS
Editable cells start at B5. Enter NEW unique counts per week; do not double-count returning users.
Week ending | Qualified interviews (info) | Recent pain (info) | Alpha started (info) | Alpha completed (info) | New unique installs | New activated | New users 2nd use | New paying customers | Gross USD | Refunds USD | Fees USD | Critical incidents | Evidence / channel notes
2026-10-25
2026-11-01
2026-11-08
2026-11-15
2026-11-22
2026-11-29
WARNING: Blank means not reported. A zero means reviewed and confirmed zero. Entries in B–E are informational; dashboard uses Interview Log and Alpha Testers.

## Interview Log
CUSTOMER DISCOVERY LOG
Use anonymized interview IDs. Do not store full names, personal emails, or proprietary code here.
Interview ID | Date | Channel / persona | Qualified? | Specific recent incident? | Incident / time lost (sanitized) | Current workaround | Top unmet pain | Would pay after demo? | Evidence / notes

## Alpha Testers
ALPHA TESTER LOG
One tester per row. Completion means independently finished inspect → claim → check → handoff.
Tester ID | Date | Qualified? | Completed scenario? (notes) | Completed? | Usability issue | Would use again? | Safety issue? | Evidence / follow-up

## Risk Register
RISK REGISTER
Owner reviews risks each Monday; every safety incident blocks release until resolved.
Risk ID | Risk | Likelihood | Impact | Mitigation | Trigger / evidence | Owner | Status
R1 | Existing tools already solve buyer pain | High | High | Validate unmet gap with real users | <5 verified pain interviewees | Founder | Open
R2 | Unexplainable false positives | Medium | High | Explain warnings; fixtures and label confidence | >20% false warnings on labeled alpha fixtures | Engineering | Open
R3 | Missed overlap gives false safety | Medium | High | Advisory-only; edge cases; no safety guarantee | Known overlapping fixture not detected | Engineering | Open
R4 | Secret leakage / destructive repo ops | Low | Critical | Offline default; explicit writes; secure process execution | Any unapproved repo write or egress | Founder | Open
R5 | No reason to pay over free tools | High | Medium | Test differentiated paid feature and support | No credible paid signals after qualified demos | Founder | Open
R6 | Too much engineering before demand proof | Medium | High | G1 gate first; cap P0 scope | UI/backend built before validated gap | Founder | Open
R7 | Company/third-party license conflicts | Medium | High | Synthetic examples; provenance review | Unapproved reuse of proprietary material | Founder | Mitigated: PolyForm Shield on public repo; Pro private; provenance notes record the MIT window (0 clones)
R8 | Radar or Anthropic absorbs the handoff / merge-readiness layer | Medium | High | Own the preflight ownership layer first; integrate with Radar rather than compete if it gains traction | Radar stars/releases; Anthropic changelog (worktree + TaskCompleted hooks) | Founder | Open

## Decision Log
DECISION LOG
Capture every gate result, product pivot, scope or target change with rationale and evidence.
Decision ID | Date | Gate | Decision | Evidence & rationale | Decision owner | Next action / due
D1 | 2026-10-17 | G1 | GO to G2; wedge = task-level path ownership + preflight overlap (P3, P1, P7); handoff/merge-readiness fast-follow | Desk research: A+B empty across 20 tools; Radar (Oct 2026) already ships test-evidence gate. docs/RESEARCH_G1.md | Founder | Start G2 from session-agents mod
D2 | 2026-10-20 | G1 | Drop the interview round; accept H1 on desk research + founder incidents | Sourced evidence (41.7% cross-agent conflict rate; 35–69% unverified test claims) and the mod itself was built from founder incidents | Founder | Feedback from G3 alpha testers
D3 | 2026-10-20 | G5 | Pricing: low price, volume ($5–$12 one-time or a few $/month); test two points at G5 | Comparables: SessionWatcher $6.99/$14.99; Vibe Kanban failed at $30/user | Founder | Define Pro boundary before G5
D4 | 2026-10-20 | G2 | Adopt session-agents mod as the interactive surface; CLI and mod share .guardian/tasks.json | docs/MOD_REVIEW.md; live ownership hold observed 2026-10-20 | Founder | G2-06..09
D5 | 2026-10-20 | G2 | G2 closed with evidence; G3–G6 artifacts prepared; G3–G6 exits stay open until real testers, installs and buyers exist | docs/SAFETY_AUDIT.md, CI, release v0.1.0; MASTER_PLAN §5 pass criteria need external evidence that cannot be produced internally | Founder | Send alpha outreach (G3-02); record demo clips (G2-09)
D6 | 2026-10-20 | G4/G5 | Relicense public repo MIT → PolyForm Shield 1.0.0; paid features in private repo workspace-guardian-pro; drop awesome-claude-code channel | Founder requirement: nobody may clone the project and offer it as their own. GitHub traffic at change: 0 clones, 0 forks, 0 stars. Shield allows use at work, forbids competing products. | Founder | Create pro repo skeleton + license-key design (done 2026-10-20)
D7 | 2026-10-23 | G5 | Checkout provider: Lemon Squeezy; manual key fulfilment during pilot; webhook signer deferred | Merchant of record (tax), file delivery, two price variants on one product; 3-buyer pass mark makes manual fulfilment fine | Founder | Set up store per docs/CHECKOUT_LEMONSQUEEZY.md; test purchase + refund
D8 | 2026-10-23 | G5 | Founding price: Pro $1/month for first 30 days or 100 buyers, grandfathered; free core stays free and public | Paid users are the feedback cohort; no marketplace can sell a Claude Code mod; directory lists free plugins only; Lemon Squeezy nets ~$0.45/$1 | Founder | Create store with variant F; launch posts carry the founding line
D9 | 2026-10-23 | G4/G5 | Sell only via Lemon Squeezy; list a free SKILL.md wrapper on Agensi.io after launch (discovery for Cursor/Codex users), never Pro | Agensi sells SKILL.md files only, via its own MCP connector, 30% fee; numbers self-reported; our Pro is a package + key | Founder | Add backlog G4-04 after launch

## Competitors
COMPETITOR MATRIX
Initial evidence-based seed list. Expand to 10+ verified direct/adjacent competitors during G1.
Product | Type | Native parallel sessions | Overlap preflight | Evidence handoff | Pricing / license | Evidence link | Gap to verify
Claude Code native | First-party CLI | Yes (worktrees, teams) | Research | Research | Depends on Claude plan | https://support.claude.com/en/articles/14554000-claude-code-power-user-tips | How independent sessions share task claims
Conductor | GUI workspace manager | Yes | Research | Workspace notes + checks | Verify current plan | https://www.conductor.build/docs/guides/parallel-agents/run-multiple-claude-code-sessions | Pre-branch task scope vs post-change diff
Claude Squad | TUI session manager | Yes (tmux/worktrees) | Research | Research | AGPL-3.0 repo license | https://github.com/smtg-ai/claude-squad | Structured collision prevention vs session status
Vibe Kanban | Agent Kanban/workspaces | Yes | Research | Diff review | Project sunsetting | https://vibekanban.com/ | Community fork, maintenance and feature overlap
worktrunk (wt) | Worktree CLI for agents | Yes (worktrees) | No | No (merge-tree conflict flag only) | Free, MIT/Apache; v0.80 Sep 2026 | https://worktrunk.dev/list/ | merges itself; Guardian report as pre-merge hook
Radar | Local merge gate + MCP | n/a | Partial (post-hoc drift) | Yes: PASS/FAIL/NOT VERIFIED, Radar-Verified trailer | Free, MIT; created 2026-10-09, 2 stars | https://github.com/Jake-Network/radar | closest on C/D; no path ownership
Superset (YC) | Agent IDE | Yes | No (states worktrees do not prevent conflicts) | No | Free; Pro $20/user/mo | https://superset.sh/pricing | needs-rebase marker only
Crystal → Nimbalyst | Desktop session manager | Yes | No | No | MIT; Teams $20/user | https://nimbalyst.com | isolation only
ccmanager | TUI session manager | Yes | No | No | Free, MIT; v4.4.8 Oct 2026 | https://github.com/kbwo/ccmanager | copies session data between worktrees
agent-of-empires | Rust tmux manager | Yes | No | No | Free, MIT; v1.20 Oct 2026 | https://github.com/agent-of-empires/agent-of-empires | diff view only

## Definitions
METRICS & CONTROL DEFINITIONS
Use the same definitions in every weekly review. These rules prevent inflated numbers.
Term | Exact meaning | Data entry instructions
Qualified interview | Used 2+ AI coding sessions in one repo within past month, completed interview | Interview Log D = Yes
Recent verified pain | Qualified user describes a real incident in last 30 days | Interview Log E = Yes + sanitized notes
Alpha completion | Finished four-step scenario with no operator takeover | Alpha Testers E = Yes
Verified new install | Distinct new installer confirmed; not downloads or GitHub stars | Weekly Metrics F; deduplicate across weeks
New activation | New user generated a meaningful risk report | Weekly Metrics G; count each user once
New repeat user | Distinct activated user returns in another session/day | Weekly Metrics H; first repeat only
New paying customer | Distinct non-refunded real paying customer | Weekly Metrics I; remove refunded sale from count
Gross USD | Collected sales before fees/refunds | Weekly Metrics J
Net receipts | Gross minus refunds and payment processor fees, not profit | Weekly Metrics J minus K minus L
Critical safety incident | Destructive unapproved change, secret disclosure, or unsafe command execution | Weekly Metrics M; any value >0 blocks rollout
Gate pass | Owner explicitly checks deliverables and evidence | Milestones F = Passed only after review
Not started vs zero | Blank metrics indicate missing report; zero = observed zero | Do not prefill zeros for future weeks
Weekly cadence | Monday plan; Friday review and decision log | Update sheet data with linked evidence
Working assumptions | Targets are business validation hypotheses | Revisions must be logged in Decision Log